## Slide 1: For the Technology Track

## Slide 2: Table of Contents
Phase 1 – Scope 9
Functional Scope Workshop 10
Data Conversion & Interface Scope Workshops 11
Technology Overview Workshop 12
Technology Architecture Workshop 13
Hardware Sizing Process 14
Technology Scope Workshop 15
Engagement Workshop 16
Phase 2 – Design 17
Initial Planning & Methodology Workshop 18
Solution Overview Education Workshop 19
Implementation Tools Installation Workshop 20
Technology Architecture Design Workshop 21
Technology Project Management Workshop 22
Project Management Workshop 23
Steering Committee Workshop 24
Planning Workshop 25
Technology Planning Workshop 26
Phase 3 – Configure 27
Methodology Workshop 28
Technology Methodology Workshop 29
Change Management Action Lab 30
Operations Support Action Lab 31
Print Management Action Lab 32
Security Action Lab 33
Installation Planning Workshop 34
Installation Workshop 35
System Administration Workshop 36
Operations Support Workshop 37
Presentation Layer Workshop 38
Technology Change Management Workshop 39
Batch Processing Workshop 40
Print Management Workshop 41
High Availability Workshop 42
Enterprise Management Workshop 43
Phase 4 – Go-Live 44
Production Configuration Workshop 45
Readiness Assessment Workshop 46
Security Workshop 47
Disaster Recovery Planning Workshop 48
System Test Workshop 49
Performance Tuning Workshop 50
Production Conversion Workshop 51
Phase 5 – Optimize 52
Technology Support Center Workshop 53
Performance Management Workshop 54
Solution Maintenance Workshop 55
Transition Workshop 56
Solution Upgrade Scenario 57-59
Platform Conv. Scenario 60-62

## Slide 3: OneMethodology Overview
OneMethodology is the approach used by J.D. Edwards to implement our software solutions.
The methodology is founded on the concept that every task within the implementation must be associated to a specific activity.
Each activity comes equipped with the intellectual property needed by the project team to complete all of the necessary implementation activities. The intellectual property generally consists of:
Process flow models
Objectives and deliverables
Agenda
Invitees (based on customer roles)
Database of discussion items (including implications)
Operational data
AutoPilot scripts to load data
Scripts to validate test transactions
Customizable, role-based end-user training materials
OneMethodology is an activity based implementation approach that employs a collection of activities to organize work, capture and resolve issues, and quickly make and implement decisions.

## Slide 4: OneMethodology Implementation Phases
Scope
A set of workshops that gather the scope and value statements for the project
Design
A set of workshops where the project team defines the business processes to support the agreed project scope
Configure
A set of workshops and action labs that configure, test, and validate the solution using the customer’s specific data and processes
Go-Live
A set of workshops that prepare the system for live transaction processing and trains the users in the use of the system
Optimize
A set of workshops designed to provide knowledge transfer to users so they can further extend the business processes implemented during initial live processing
OneMethodology consists of five major phases:

## Slide 5: Workshops and Action Labs
Workshops
Workshops are typically used to perform one of the following:
  Design, customize, or build workshop deliverables
  Knowledge transfer and/or training
  Project management and change management
Steps of the Workshops may be performed over different periods of time, and may involve different participants.
Within OneMethodology two types of activity are used to define the business process flow, and configure the supporting system.
All activities have objectives and specific inputs/outputs and deliverables.
Workshops are comprised of four distinct steps:
  Prepare Gather the designated materials to support the execution of the workshop.
  Build Develop the specific workshop deliverables with core team members.
  Present Present the deliverables to the wider business audience.
  Craft Refine the deliverables to include improvements from the Present step.

## Slide 6: Workshops and Action Labs
Action labs are characterized by the presentation of a pre-configured solution or standard that is provided by J.D. Edwards.
Action labs are designed to facilitate rapid decision making. Therefore, the conduct step of action labs is performed over a continuous time period, and usually involves a single set of participants.
An action lab comprises three distinct steps:
  Prepare Gather the designated materials to support the execution of the action lab.
  Conduct Present and discuss the J.D. Edwards’ standards and/or pre-configured solutions with the customer team.
  Craft Execute the action lab decisions.
Action Labs
Within OneMethodology two types of activity are used to define the business process flow, and configure the supporting system.
All activities have objectives and specific inputs/outputs and deliverables.

## Slide 7: Customer Involvement
Level of Customer Involvement
Low
Medium
High
Task | Low Involvement |  | Medium Involvement |  | High Involvement | 
 | JDE | Client | JDE | Client | JDE | Client
Software Configuration |  |  |  |  |  | 
Activity Facilitation |  |  |  |  |  | 
Process Validation |  |  |  |  |  | 
Pre-Live Power User Training |  |  |  |  |  | 
Participation
High
Medium
Minimum
Notes: Level 2 appears on this slide.
Majority of clients would go for this option, I.e. we do the set-up top enable rapid go-live, but they get a comfort factor by processing test transactions.

## Slide 8
Roles
Business Objectives
Cost and Resource Time Estimates
Process Scenarios
Activities
Process Components
Topics
Project Scoping
Project Planning
Issues
Project Management Tool

## Slide 9: OneMethodology Technology Track – Scope Phase Overview
SCOPE
Phase
The Scope phase of OneMethodology is comprised of a set of workshops that gather the scope and value statements for the project.
The following activities form the basis of the Scope phase:
Functional Scope Workshop
Technology Scope Workshop
Engagement
Workshop
Technology Overview Workshop
Technology
Architecture
Workshop
Design
Phase
Hardware
Sizing Process
Data Conversion
Scope Workshop
Interface Scope Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 10: OneMethodology Technology Track – Scope Phase Overview
Key Objectives
Establish a connection between business processes and functional requirements to the client’s goals and business objectives
Agree on business processes and functional requirements
Demonstrate the connection between the selected business processes, functional requirements and the resulting action labs and workshops
Concept
Develop the scope of the functional solution required to meet the client’s goals and business objectives, which in turn assists in the definition of the technology scope and project plan.
Functional Scope Workshop
Deliverables
Functional scope definition
Preliminary resource requirements
List of required workshops and action labs
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 11: OneMethodology Technology Track – Scope Phase Overview
Key Objectives
Define the scope of the data conversion activities.
Define any interface requirements to legacy systems.
Outline the technical strategy for data conversions and/or interfaces
Concept
Develop the scope of the data conversion and interface efforts required to support the functional scope and deliverables.
Deliverables
Preliminary Resource Requirements
Data conversion/interface strategy document
Data conversion/interface scope document
List of required workshops/action labs
Develop the scope of the functional solution required to meet the client’s goals and business objectives, which in turn assists in the definition of the technology scope and project plan
Data Conversion and Interface Scope Workshops
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 12: OneMethodology Technology Track – Scope Phase Overview
Key Objectives
Establish key technology contacts
Overview product architecture, components, features, and options
Review the Scope phase activities
Begin scope definition process for enterprise architecture and implementation requirements
Begin the hardware sizing process
Concept
Present product architecture, key features and concepts, supported technologies, and OneMethodology while gathering initial project scope and technology requirements.
Deliverables
Technology requirements survey
Technology overview materials
Sizing documents
Summary of Scope phase workshops and action labs
Technology Overview Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 13: OneMethodology Technology Track – Scope Phase Overview
Key Objectives
Develop an enterprise computing architecture
Decide on server and database platform options
Identify high availability, disaster recovery, and enterprise management requirements
Leverage existing technologies and skills
Identify gaps between enterprise architecture and existing systems and skills
Provide additional input and guidance for the hardware sizing process
Concept
Develop a high-level architecture for the enterprise-wide computing solution required to support the functional scope, data center model, corporate geography, user community profiles, and technology support requirements.
Deliverables
Technology architecture document
Technology requirements, constraints, and objectives
Technology Architecture Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 14: OneMethodology Technology Track – Scope Phase Overview
Key Objectives
Determine the disk, computing power, and memory requirements for database, enterprise, and application servers
Provide general guidelines and recommendations for server models, configuration, and options
Provide information necessary to complete hardware and 3rd party software cost estimates, contributing to solution’s the total cost of ownership (TCO) estimate
Concept
The selected J. D. Edwards Technology Alliance Partner conducts a hardware sizing exercise, to determine the size and configuration of core servers within the enterprise architecture. This process is defined and managed by the Technology Alliance Partner, usually with support from their Value Added Reseller.
Deliverables
Technology Alliance Partner sizing response document
Value Added Reseller configuration and services proposal
Hardware Sizing Process
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 15: OneMethodology Technology Track – Scope Phase Overview
Key Objectives
Establish a connection between business processes and technology requirements to the client’s goals and business objectives
Establish the relationship between the technology, data conversions/interfaces, and application tracks of the implementation project
Identify support requirements, skill set requirements, and project risks
Determine support partners and lines of ownership
Determine scope and phasing of the technology project
Concept
Develop the scope of the technology solution required to support the functional scope and requirements as well as to meet any technology-specific goals and objectives.
Deliverables
Technology scope definition
Preliminary resource requirements
List of required workshops and action labs
Technology Scope Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 16: OneMethodology Technology Track – Scope Phase Overview
Key Objectives
Estimate the time required to plan and execute the identified workshops and action labs
Identify consulting resources required to staff the workshops and action labs
(including project management, change management, and staff augmentation activities)
Identify client resources (by role) required to attend the workshops and action labs
Confirm the risk, issue, and change control procedures
Concept
Provide a clear estimate of the time and resources required to implement the business processes, functional enhancements, and technology frameworks identified in the Scope workshops.
Deliverables
An engagement agreement, which describes:
  Project organization structure including roles and responsibilities
  Project scope and phasing
  Resource requirements
  Time and cost estimates
  Agreed level of customer project involvement at the methodology activity level
  Risk management and change control procedures
  Power user and end user education plan
Engagement Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 17: OneMethodology Technology Track – Design Phase Overview
Milestones
Implementation
Activities
Project
Management
Operational Support
Configure
Phase
Technology
Proj Mgmt Workshop
(Recurring)
Technology Proj Mgmt…
Technology Proj Mgmt…
Scope
Phase
Implementation Tools
Live
Design
Start
Technology Proj Mgmt…
Project Planning Workshop
Technology Planning Workshop
Implementation Tools Installation Workshop
Initial Planning & Methodology Workshop
Project Mgmt Workshop (Recurring)
Steering Committee Workshop (Recurring)
Solution Overview Education Workshop
Technology Architecture Design Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 18: OneMethodology Technology Track – Design Phase Overview
Initial Planning & Methodology Workshop
Concept
Create a detailed project plan describing the schedule of activities during the Design phase.
Key Objectives
Confirm the project scope, objectives and goals as outlined in the Engagement Letter
Provide OneMethodology overview education
Confirm project roles and responsibilities
Generate a detailed Design phase project plan
Define a risk management plan
Define change control procedures
Confirm the level of customer project involvement
Deliverables
Detailed project plan covering the Design phase
Project organization chart including roles and responsibilities
Risk and issues management plan Change control procedure
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 19: OneMethodology Technology Track – Design Phase Overview
Solution Overview Education Workshop
Concept
Provide the customer's project team with an overview of the core J.D. Edwards software architectural principles.
Key Objectives
Provide education on the following items:
  System navigation
  Processing Options
  User Defined Code tables
  Batch versus Interactive jobs
  Work Center message handling
  Next number processing
Deliverables
A customer project team that is familiar with the concepts, and terms used within J.D. Edwards software
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 20: OneMethodology Technology Track – Design Phase Overview
Implementation Tools Installation Workshop
Concept
Install implementation tools in a central location for use by all project team members.
Key Objectives
Define architecture and system requirements for implementation tools
Install and configure all project tools
Define and deploy security policy for accessing tools and project data
Define remote access policy and implement access solution
Educate technology project team on support procedures for implementation tools
Deliverables
Implementation tools ready for use
Implementation tools support guide
Remote access setup guide
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 21: OneMethodology Technology Track – Design Phase Overview
Technology Architecture Design Workshop
Concept
Refine the high-level architecture for the enterprise-wide computing solution. Create model architecture if multiple installs will be necessary. Determine details of architecture that apply to cost and implementation effort.
Key Objectives
Create a model data center architecture with integration solution to keep multiple data centers and software development efforts in sync
Review and refine high availability, disaster recovery, and enterprise management requirements
Determine detailed user profiles and counts, transaction volumes, batch schedules and batch processing volumes
Determine output management requirements and level of effort
Review all software integration points and interfaces, update system architecture
Incorporate high-level change management and testing requirements into system architecture
Determine net-change to existing infrastructure
Agree on a phased plan for constructing the enterprise-wide technology solution
Deliverables
Revised and expanded technology architecture document
Revised and expanded technology requirements, constraints, and objectives
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 22: OneMethodology Technology Track – Design Phase Overview
Technology Project Management Workshop
Concept
A recurring set of Workshops designed to manage technology project activities, status, and exceptions. These workshops are related and subordinate to the Project Management Workshops.
Key Objectives
Track the progress of the project against the plan
Manage unresolved issues associated with completed activities
Manage issues related to project resources
Manage issues related to operational support
Manage requests from the applications and data conversions/interfaces teams
Review open Global Support Services calls and Software Action Requests
Manage requests for J.D. Edwards software updates and service packs
Deliverables
Periodic status reports
Updated issue database
Updated project plan
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 23: OneMethodology Technology Track – Design Phase Overview
Project Management Workshop
Concept
A recurring set of workshops designed to manage project activities, status, exceptions and scope.
Key Objectives
Track the progress of the project against the plan
Manage unresolved issues associated with completed activities
Manage issues related to project resources
Deliverables
Periodic status reports
Updated issue database
Updated project plan
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 24: OneMethodology Technology Track – Design Phase Overview
Steering Committee Workshop
Concept
A recurring set of Workshops designed to manage project goals and strategic direction.
Key Objectives
Review progress against major milestones
Review periodic and cumulative project expenditure against budget
Review project change requests
Review major project issues and risks
Deliverables
Change request decisions
Strategic direction to the project team
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 25: OneMethodology Technology Track – Design Phase Overview
Project Planning Workshop
Concept
Develop a detailed implementation management plan based on the formal J.D. Edwards services Proposal and Engagement letter. This covers applications and interfaces, producing a required milestone schedule for the technology project.
Key Objectives
Reinforce OneMethodology to the customer project team
Demonstrate how the project scope will drive all subsequent activities
Confirm project roles and responsibilities
Generate a detailed, resourced project plan
Define a risk management plan
Define change control procedures
Confirm the level of customer project involvement
Deliverables
Detailed project plan including the level of customer involvement at the specific activity level
Project organization chart including roles and responsibilities
Risk and issues management plan
Change control procedure
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 26: OneMethodology Technology Track – Design Phase Overview
Technology Planning Workshop
Concept
Develop a detailed implementation management plan based on the project scope, resource roles, and time estimates outlined in the formal J.D. Edwards services Proposal and Engagement letter.
Key Objectives
Reinforce OneMethodology to the customer project team
Demonstrate how the project scope will drive all subsequent activities
Confirm project roles and responsibilities, level of customer involvement
Generate a detailed, resourced project plan
Define a risk management plan
Define change control procedures (at the project management level)
Confirm detailed equipment and software schedule for the prototype environment
Deliverables
Detailed project plan including the level of customer involvement at the specific activity level
Project organization chart including roles and responsibilities
Risk and issues management plan
Change control procedures
Detailed system requirements for the prototype environment
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 27: OneMethodology Technology Track – Configure Phase Overview
Milestones
Implementation
Activities
Project
Management
Operational Support
Project Mgmt Workshop (Recurring)
Go-Live
Phase
Technology
Proj Mgmt Workshop
(Recurring)
Technology Proj Mgmt…
Technology Proj Mgmt…
Presentation Layer
Workshop
Technology
Change Mgmt
Workshop
Batch Processing Workshop
Design
Phase
Project Environments
Live
Project
Start
Change Mgmt Solution
Live
Technology Proj Mgmt…
High Availability Workshop
Enterprise Management Workshop
Operations Support Workshop …
Technology
Methodology
Workshop
Security Action Lab
System
Admin
Workshop
Operations Support Action Lab
Print Management Workshop
Methodology Workshop
Project Hardware
Installed
Security
Workshop
(Go-Live Phase)
Print Management Action Lab
Change Management Action Lab
Installation
Workshop
Installation Planning Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 28: OneMethodology Technology Track – Configure Phase Overview
Methodology Workshop
Concept
Provide detailed training on the methodology, including client roles and
responsibilities that will be used to deliver the solutions identified during
the scope workshop.
Key Objectives
Brief the JDE project team on the project’s objectives and scope.
Provide a clear understanding of the methodology to the project team.
Provide the client with a detailed understanding of the Prepare,
Build, Present, and Craft steps associated with workshops.
Provide the client with a detailed understanding of the Prepare, Present, Discuss, and
Craft steps associated with action labs.
Educate the whole project team on the issue management and scope control procedures
Deliverables
Project team members trained in the methodology
Preparation requirements for the workshops and action labs
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 29: OneMethodology Technology Track – Configure Phase Overview
Technology Methodology Workshop
Concept
Provide detailed training on technology-specific aspects of the methodology, including roles and responsibilities of the technology team, milestone deliveries, and operational support requirements
Key Objectives
Review the operational support requirements and dependencies to the applications and data conversions/interfaces project teams
Educate project team on the handling, routing, and escalation of issues and requests through the technology help desk
Provide the client with a clear understanding of Global Support Services call submission, tracking, escalation, and Software Action Requests
Review the benefits and use of the support assistant tool
Review the benefits and requirements of remote access support for Global Support Services and the J.D. Edwards consulting team
Educate project team on the impact of software updates, service packs, and the deployment process
Deliverables
Project team members trained in operations support methodology
Remote access requirements for extended implementation support
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 30: OneMethodology Technology Track – Configure Phase Overview
Change Management Action Lab
Concept
Present and refine the change management architecture and process flows that will control all development, testing, prototyping, and release activities. Change management process flows encompass physical infrastructure, software, software configuration, source code, and data management.
Key Objectives
Determine what components of the solution will be controlled through change management
Define the required change management activities and working environments for completing all change management activities
Agree on the review, approval, deployment, and maintenance policies that will be required
Define the change management architecture for handling the development, review, and approval of all changes to the production environment
Develop a schedule for releasing change management capability to the project teams
Define the roles, procedures, tracking documents, and tools that will be involved in change management
Deliverables
Change management design guide
Initial change management procedures guide
Data management action plan
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 31: OneMethodology Technology Track – Configure Phase Overview
Operations Support Action Lab
Concept
Present and refine the details of the operations support processes that will be used to support the implementation project, as well as underlying systems. Define the structure and required data elements associated with the operations support processes.
Key Objectives
Review and refine the operational support processes that will be used to maintain healthy project systems and support all implementation activities
Determine what tools and forms will be used to submit and manage help desk issues and requests
Agree on how help desk issues will be routed and escalated
Agree on how help desk requests will be routed, escalated, and approved
Determine what support tools and remote access methods will be available for J.D. Edwards Global Support Services and off-site technology team members
Deliverables
Selected tools and forms for managing operations requests and issues
Defined process flows for the operations support help desk
Operations support procedures guide
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 32: OneMethodology Technology Track – Configure Phase Overview
Print Management Action Lab
Concept
Present options regarding printing and output management. Determine an overall approach to output management. Define printer configuration, print queues, output transformation, and output routing requirements for all output destinations.
Key Objectives
Review options and refine the requirements and approach for a system-wide print and output management plan
Determine requirements for defined printers
Define requirements for defined print queues
Develop a detailed output management plan that defines all required forms of output, transformation requirements, output routing and destinations, and printer device configuration
Deliverables
Output Management Requirements
Completed printer and print queue configuration spreadsheets ready for loading by AutoPilot
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 33: OneMethodology Technology Track – Configure Phase Overview
Security Action Lab
Concept
Present and refine the details of the security policy that will be required to control access to sessions, applications, and data. Define the structure and required security records associated with role, application, and data security.
Key Objectives
Review options and refine the architecture and approach for a system-wide security plan
Determine requirements for sign-on security
Define requirements for activity tracking
Define external security plan – network, operating system, and database
Develop a detailed security plan with configuration records by role and application
Deliverables
Security policy guide
Completed security data spreadsheets ready for loading by AutoPilot
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 34: OneMethodology Technology Track – Configure Phase Overview
Installation Planning Workshop
Concept
Communicate options and confirm understanding of technology architecture to develop a detailed installation plan. This builds upon the enterprise architecture and determines all detailed information necessary to install and configure the J.D. Edwards software solution.
Key Objectives
Ensure agreement on technology expectations of the implementation, specifically: performance, structure, design, and IT practices
Establish support contacts and computing environment details necessary to complete the J.D. Edwards software install
Verify change management approach and requirements
Create a detailed installation plan
Review all hardware setup and pre-installation configuration steps
Determine required J.D. Edwards software products and verify they have arrived
Detail any equipment, software, and procedures necessary for remote and on-site support
Audit the installed computing environment to validate the pre-install plan is complete
Deliverables
Detailed J.D. Edwards system design document and installation plan
Environment preparation requirements and steps
Environment audit results and issues list
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 35: OneMethodology Technology Track – Configure Phase Overview
Installation Workshop
Concept
Install and deploy J.D. Edwards software to all systems needed throughout the implementation project. Configure all environments that will be needed to support project activities.
Key Objectives
Install J.D. Edwards software on the project hardware
Apply and deploy all J.D. Edwards software updates that are required for initial project activities
Install all secondary products that will be needed such as Auto Pilot and Vertex
Configure all environments that will be required for project activities by the applications and data conversions/interfaces teams
Deliverables
Installed J.D. Edwards software environments
Surface test checklist
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 36: OneMethodology Technology Track – Configure Phase Overview
System Administration Workshop
Concept
Configure all runtime services and support components necessary for the applications and data conversions/interfaces teams, define and establish all recurring system administration procedures, mentor technology team on administrative duties.
Key Objectives
Ensure all required setup is complete, including:
  Sign-on security and other J.D. Edwards software services
  Printing Services
  Basic change management
Setup and verify backup and recovery tools and procedures
Setup all user accounts that will be needed for the applications and data conversions/interfaces teams
Configure basic system security to restrict access for the implementation teams and user roles
Establish remote access for Global Support Services and remote technology team members
Deliverables
Configured J. D. Edwards software environments and services
Client IT staff trained in basic system administrative functions
Recurring support procedures established
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 37: OneMethodology Technology Track – Configure Phase Overview
Operations Support Workshop
Concept
Provide ongoing operations and help desk support activities for the remainder of the implementation project. This is primarily covered by the client’s IT staff, with possible planned consulting augmentation for specific planned tasks or to accommodate an overburdened IT department.
Key Objectives
Establish a technology help desk for the project, document support procedures
Provide daily help desk support for project teams
Provide daily systems administration support
Manage technology issues and requests from the project teams
Perform installation and deployment of software patches and service packs as required by project teams
Support recurring code and data change management activities
Perform regular system maintenance and backup/recovery activities
Deliverables
Project technology help desk established
J.D. Edwards software environments open to project teams
Regular activity and issues logs to the project management team
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 38: OneMethodology Technology Track – Configure Phase Overview
Presentation Layer Workshop
Concept
Design and implement thin-client solutions to support remote project team members, remote development activities, and prepare for support of production users.
Key Objectives
Determine detailed configuration requirements of presentation server farm(s)
Install and configure presentation server farm(s) and setup alternate environments
Educate client on special deployment and administrative procedures related to J.D. Edwards software on presentation servers
Tune servers for performance and scalability
Establish recurring maintenance procedures
Deliverables
Client IT staff trained in basic presentation servers administrative functions
Detailed presentation servers architecture document
Presentation server environments live for project teams and remote development activities
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 39: OneMethodology Technology Track – Configure Phase Overview
Technology Change Management Workshop
Concept
Refine and implement change management procedures to document and control all activity resulting in a change to the production system. Provide the project teams with knowledge in the use of change management tools and outline change migration and deployment strategies.
Key Objectives
Establish standards and procedures for development, system setup and process changes
Establish and implement a change migration and deployment strategy for each change management environment
Establish and implement an environment management strategy
Educate project teams on the use of change management tools and procedures
Deliverables
Refined change management procedure guide
Change management request and tracking forms
Software migration and deployment guide
Change management tools configured and active for general use
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 40: OneMethodology Technology Track – Configure Phase Overview
Batch Processing Workshop
Concept
Develop and implement a detailed batch scheduling and processing solution for all environments. Establish operating guidelines for day and night batch processing.
Key Objectives
Establish operational requirements, guidelines, and restrictions for daily and nightly batch processing
Gather batch requirements from project teams and establish a nightly batch processing schedule
Configure batch queues, multi-processing, prioritization, and the batch scheduler tool
Conduct initial performance tuning and establish procedures for batch testing and tuning
Deliverables
Detailed batch configuration and management document
Production batch schedule with dependencies and time table
Advanced batch system available for use by project teams
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 41: OneMethodology Technology Track – Configure Phase Overview
Print Management Workshop
Concept
Develop and implement a detailed printing solution that includes printer types and definitions, output management, destination routing, and remote printing solutions.
Key Objectives
Define all print output types that are required, including output post-processing requirements
Determine all production printers and determine configuration requirements
Define output routing requirements for both interactive and batch printing activities
Develop and test remote printing solutions
Configure and test all components of the overall print management solution
Deliverables
Detailed printing architecture, configuration, and support document
Printing and print routing solutions configured and tested
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 42: OneMethodology Technology Track – Configure Phase Overview
High Availability Workshop
Concept
Develop a detailed high availability architecture and process plan. Implement high availability components for eventual use with the production systems.
Key Objectives
Verify production high availability requirements and service level agreements
Detail all high availability components and support procedures
Install and configure all high availability components including:
  Clustering software and hardware
  Load balancing software and hardware
  J.D. Edwards software-based solutions
Perform tests of all high availability components
Deliverables
Detailed high availability architecture and procedures document
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 43: OneMethodology Technology Track – Configure Phase Overview
Enterprise Management Workshop
Concept
Develop the production solution management plan that covers help desk, recurring administration, and established operating procedures. Develop and implement a plan for automated monitoring, alerting, and capacity planning.
Key Objectives
Determine production help desk structure, additional IT training requirements, escalation and management procedures, and expanded change management procedures
Detail all monitoring, alerting, disaster/recovery, and capacity planning requirements
Implement and test monitoring and alerting solutions, including the integration of 3rd party products such as BMC Patrol, Tivoli, and HP OpenView
Deliverables
Enterprise management design and procedures document
Production help desk support document
Production administration and maintenance document
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 44: OneMethodology Technology Track – Go-Live Phase Overview
Milestones
Implementation
Activities
Project
Management
Operational
Support
Production Configuration Workshop
Optimize
Phase
Production Conversion Workshop
System Test
Workshop
Performance Tuning
Workshop
Configure
Phase
Operations Support Workshop (Continued) …
Project Mgmt Workshop (Recurring)
Technology
Proj Mgmt Workshop
(Recurring)
Technology Proj Mgmt…
Technology Proj Mgmt…
Technology Proj Mgmt…
Production
Go-Live
Production Hardware
Installed
Production Environments
Active
Security
Workshop
Readiness Assessment
Workshop
Disaster Recovery Planning Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 45: OneMethodology Technology Track – Go-Live Phase Overview
Production Configuration Workshop
Concept
Configure the production environment for live transaction processing.
Key Objectives
Verify that all production servers are properly configured
Complete the configuration of the production J.D. Edwards software environments in preparation for the System Test Workshop
Perform a technology sweep of all the technology components
required to support live processing
Deliverables
Production configuration document
All code and system objects promoted to Production and deployed
Production environments available to project teams
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 46: OneMethodology Technology Track – Go-Live Phase Overview
Readiness Assessment Workshop
Concept
Verify the readiness of the IT staff, procedures, and physical systems to support production use of the solution. Provide a risk-based issues list and action plan to manage the completion of the project and transition into production use. This activity is performed across all aspects of the project, but only technology activities are detailed below.
Key Objectives
Interview IT support staff, review competed training
Review production support procedures and help desk solution
Review open issues and determine impact and risk to production use
Conduct a physical audit of all systems and administration tools for proper configuration
Compile a list of open issues and assign level of risk to production use
Deliverables
Gaps in activity completion, support procedures, and staff preparedness
Concerns and risks to production use of the solution
Action plan to address identified gaps and issues
Overall recommendation on whether to proceed with production go-live date
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 47: OneMethodology Technology Track – Go-Live Phase Overview
Security Workshop
Concept
Configure sign-on and application security for production users and environments. Define and apply security policies for supporting computing components and services.
Key Objectives
Establish enterprise-wide security requirements/policies and develop a security plan
Gather user roles and application security requirements from project teams
Define all security policies and requirements for supporting components (networking, databases, operating systems, etc.)
Establish all production user profiles and security policies
Configure and test security for supporting components
Deliverables
Enterprise-wide security policy document
J.D. Edwards software security design document
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 48: OneMethodology Technology Track – Go-Live Phase Overview
Disaster Recovery Planning Workshop
Concept
Determine disaster recovery requirements, plan the architecture of the disaster recovery solution, and document the recovery procedures. Determine change management procedures needed for the disaster recovery solution and update the change management procedures guide.
Key Objectives
Define strategy and requirements for disaster recovery plan
Determine architecture requirements
Build a set of maintenance and cutover procedures
Identify impact of disaster recovery plan on existing change management plan
Deliverables
Disaster recovery design document
Updated change management procedures to support disaster recovery plan
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 49: OneMethodology Technology Track – Go-Live Phase Overview
System Test Workshop
Concept
Test the expected transaction loads (interactive and batch) on the production environment so that system functional and stress-based issues can be identified and addressed prior to production go-live.
Key Objectives
Develop functional scripts that will accurately simulate the expected
transaction steps and volumes during production processing
Run interactive and batch scripts to stress the system and validate accurate completion of critical business processes
Deliverables
Production environment tested as configured for live processing
Documented list of functional and stress-based issues that were identified and resolved
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 50: OneMethodology Technology Track – Go-Live Phase Overview
Performance Tuning Workshop
Concept
Simulate production interactive and batch loads in order to tune all components of the production system in preparation of production go-live. This includes terminal servers, web servers, databases, operating systems, and J.D. Edwards software services.
Key Objectives
Establish proper monitoring tools to measure the runtime performance of critical system components – networks, servers, databases, etc.
Develop and run both interactive and batch scripts to stress all components of the production solution
Review performance results, apply tuning techniques as necessary
Deliverables
Production environment tuned for anticipated transaction loads and target response times
Documented list of all configuration changes made to tune the solution
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 51: OneMethodology Technology Track – Go-Live Phase Overview
Production Conversion Workshop
Key Objectives
Create a detailed conversion plan for loading setup and transactional data into the Production environment
Migrate all system objects, data, and code from the Integration Test environment to the Production environment
Verify the conversion plan meets any applicable constraints placed upon the Production Conversion process
Build, test, and deploy final production packages
Execute the plan to populate the Production environment with setup and transactional data
Concept
Review and finalize the migration of data and code to the production environment.
Implement the conversions created during the Data Conversion / Interface Workshop and load setup tables into the Production environment.
Begin production use of the solution.
Deliverables
A list of J.D. Edwards Production tables detailing the loading method for data
A detailed Production Data Conversion plan that is tested and verified
A Production environment with setup and transactional data
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 52: OneMethodology Technology Track – Optimize Phase Overview
Milestones
Implementation
Activities
Project
Management
Operational
Support
Technology Support Center Workshop
Transition Workshop
Go-Live
Phase
Project Mgmt Workshop (Recurring)
Technology
Proj Mgmt Workshop
(Recurring)
Technology Proj Mgmt…
Technology Proj Mgmt…
Operations Support Workshop (Continued)
Project
Finish
Performance Management Workshop
Solution Maintenance Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 53: OneMethodology Technology Track – Optimize Phase Overview
  Technology Support Center Workshop
Concept
Provide initial staffing and knowledge transfer to establish an internal support center that will have the ability to resolve issues using client personnel and J.D. Edwards’ Global Customer Support.
Key Objectives
Establish J.D. Edwards’ staffed support structure for the Optimize and Extend phases of the project
Establish client support structure and team for ongoing support
Train client support team on support process and tools
Deliverables
J.D. Edwards’ solution experts to provide support during the Optimize and Extend phases of the project
Trained client support personnel
Established ongoing production support plan and procedures
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 54: OneMethodology Technology Track – Optimize Phase Overview
  Performance Management Workshop
Concept
Develop system management plan to manage performance to capacity requirements, including monitoring, tuning, archiving, and capacity planning.
Key Objectives
Define long-term capacity requirements, amount of on-line history, and policy for managing aged/completed records
Create a management plan for monitoring system use, managing performance factors, and collecting information for capacity planning
Develop a database management plan to routinely cleanse large tables and maintain optimal performance
Design and implement a data archiving solution to move aged/completed records from the active production system to an archival/history solution
Deliverables
Performance management plan
History/archival solution design
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 55: OneMethodology Technology Track – Optimize Phase Overview
  Solution Maintenance Workshop
Concept
Develop a plan for maintaining the production solution, including software updates and patches, custom modification cycles, and the maintenance of foundation hardware and software.
Key Objectives
Define operational requirements on modifications to the production environment
Review existing change management architecture and procedures, expand to address production maintenance requirements
Train IT staff on production maintenance procedures and techniques
Deliverables
Solution maintenance plan document
IT staff trained on maintenance procedures
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 56: OneMethodology Technology Track – Optimize Phase Overview
  Transition Workshop
  Concept
  Conduct a final review of the client project team’s readiness to assume responsibility for, and ongoing management of the implemented solution.
  Key Objectives
  Develop a plan for addressing remaining open issues and conducting Extend phase activities
  Review readiness of power users to assume primary support role
  Identify additional training requirements to support Extend phase activities and schedule training
  Formally close the implementation project
  Deliverables
  Extend phase project plan
  Updated issues database
  Extend phase training schedule
  Final project sign-off by client
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 57: OneMethodology Technology Track – Configure Phase – Solution Upgrade Scenario
Milestones
Implementation
Activities
Project
Management
Operational Support
Project Mgmt Workshop (Recurring)
Go-Live
Phase
Technology
Proj Mgmt Workshop
(Recurring)
Technology Proj Mgmt…
Technology Proj Mgmt…
Presentation Layer
Workshop
Technology
Change Mgmt
Workshop
Design
Phase
Upgraded Project Environments Live
Project
Start
Technology Proj Mgmt…
Operations Support Workshop …
Change Management Action Lab
Technology
Methodology
Workshop
Upgrade
Workshop
Upgrade Planning Workshop
Security Action Lab
System
Admin
Workshop
Operations Support Action Lab
Methodology Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 58: OneMethodology Technology Track – Configure Phase Overview
Upgrade Planning Workshop
Concept
Review options, define an upgrade strategy, and determine solution net-change requirements for upgrading systems and software to a new J.D. Edwards product release.
Key Objectives
Determine net-change in system requirements for new software release
Determine impact of custom modifications on the upgrade process
Develop an upgrade plan for upgrading each working environment, and a strategy for completing hardware and software upgrades by environment
Establish support contacts and computing environment details necessary to complete the J.D. Edwards software upgrade
Review all hardware setup and pre-upgrade configuration steps
Determine required J.D. Edwards software products and verify they have arrived
Detail any equipment, software, and procedures necessary for remote and on-site support
Deliverables
Detailed system requirements net-change document
Upgrade plan
Environment preparation requirements and steps
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 59: OneMethodology Technology Track – Configure Phase Overview
Upgrade Workshop
Concept
Upgrade and deploy J.D. Edwards software to all systems and environments needed throughout the upgrade project.
Key Objectives
Upgrade project environments with the new version of J.D. Edwards software
Apply and deploy all software updates that are required for initial project activities
Configure all upgrade environments that will be required for project activities by the applications and data conversions/interfaces teams
Deliverables
Upgraded project environments (not including production)
Surface test checklist
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 60: OneMethodology Technology Track – Configure Phase – Platform Conversion Scenario
Milestones
Implementation
Activities
Project
Management
Operational Support
Project Mgmt Workshop (Recurring)
Go-Live
Phase
Technology
Proj Mgmt Workshop
(Recurring)
Technology Proj Mgmt…
Technology Proj Mgmt…
Print Management
Workshop
Technology
Change Mgmt
Workshop
Design
Phase
Converted Project Environments Live
Project
Start
Technology Proj Mgmt…
Operations Support Workshop …
Technology
Methodology
Workshop
Platform Conversion
Workshop
Platform Conversion Planning Workshop
Security Action Lab
System
Admin
Workshop
Operations Support Action Lab
Methodology Workshop
Batch Processing
Workshop
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology
Print Management Action Lab

## Slide 61: OneMethodology Technology Track – Configure Phase Overview
Platform Conversion Planning Workshop
Concept
Create a migration plan for converting the existing J.D. Edwards solution to a new database and/or server hardware platform.
Key Objectives
Evaluate existing database structures, data volumes, batch schedules, and system loads
Create an installation plan for establishing new hardware and/or databases
Create migration plan for converting each working environment over to the new hardware and/or databases
Establish support contacts and computing environment details necessary to complete the platform conversion activities
Review all hardware and database pre-install setup and configuration steps
Determine required J.D. Edwards software products and verify they have arrived
Detail any equipment, software, and procedures necessary for remote and on-site support
Deliverables
Platform conversion plan
Environment preparation requirements and steps
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology

## Slide 62: OneMethodology Technology Track – Configure Phase Overview
Platform Conversion Workshop
Concept
Convert non-production J.D. Edwards software environments to a new hardware and/or database platform.
Key Objectives
Install J.D. Edwards software to new hardware and/or database platforms
Migrate data to new database platform for all non-production environments
Configure and test services for all environments that will be required for project activities by the applications and data conversions/interfaces teams
Deliverables
Converted non-production software environments
Surface test checklist
Copyright © 2002  J.D. Edwards World Source Company  J.D. Edwards Confidential  OneMethodology